## Slide 1
PROPOSAL & ACTION PLAN
New Software
Implementation
A structured 4-week plan to ensure smooth transition
and company-wide adoption
Scenario 4 | All Departments | Duration: 4 Weeks

## Slide 2
Executive Summary
About This Proposal
This proposal outlines a structured 4-week approach to rolling out new project management software across all departments. The plan is designed to maximise adoption, reduce disruption, and ensure every team member is confident using the system from day one.
The implementation is divided into four clear phases: Evaluation & Setup, Installation & Configuration, Training, and Go-Live & Monitoring. Each phase has defined tasks, owners, and measurable outcomes.
Success will be measured through adoption rates, training completion, support responsiveness, and employee satisfaction scores.
Timeline 4 Weeks
Scope All Departments
Priority High

## Slide 3
Objectives & Key Tasks
Objective
Introduce new project management software to improve efficiency across all departments, ensuring a smooth transition and strong adoption within one month.
Key Tasks
Evaluate the features and benefits of the new software
Plan the installation and configuration
Organise training sessions for all employees
Monitor initial use and provide support
Collect feedback and address issues during transition

## Slide 4
4-Week Action Plan
WEEK 1
Evaluation
& Setup
Review software features & benefits
Assess system compatibility
Assign IT leads & project owner
Create implementation checklist
WEEK 2
Installation
& Config
Install software on all devices
Configure roles & permissions
Integrate with existing tools
Run QA & testing
WEEK 3
Training
Run dept-specific sessions
Distribute user guides
Identify power users per team
Set up help desk channel
WEEK 4
Go-Live
& Monitor
Company-wide launch
Monitor usage & resolve issues
Collect feedback via surveys
Report on adoption metrics

## Slide 5
Risk Management
HIGH
Resistance to change from employees
Mitigation: Early communication, involve staff in planning, highlight personal benefits, appoint change champions per department.
HIGH
Integration failures with legacy systems
Mitigation: Conduct full system audit in week 1, run parallel testing before go-live, keep IT on standby during launch.
MED
Insufficient training coverage
Mitigation: Multiple session slots, recorded sessions for async access, designated in-team super users.
MED
Low post-launch adoption
Mitigation: Weekly adoption tracking, feedback loops, management encouragement, and quick-win showcases.

## Slide 6
Stakeholders & Responsibilities
Project Manager
Oversees the full plan, timelines, and reporting across all phases.
IT Department
Handles installation, configuration, integration, and technical support.
HR / L&D Team
Organises and delivers structured training sessions for all staff.
Department Heads
Ensure team participation, champion adoption, and monitor engagement.
All Employees
Attend training, provide feedback, and use the new system daily.
New Software Implementation Plan | Scenario 4